N2C Expanded WBS — Data Quality & Integrity Analysis Report

Source workbook: 9d102f1d-N2C_Expanded_WBS.xlsx

Analysis date: 2026-06-30

Scope: All 17 delivery WBS sheets + 4 reference tabs (Overview, Mapping, Roles & SFIA, References)

Leaf tasks analysed: 5,526

Total issues raised: 5,055 — 2 High · 5,032 Medium · 21 Low

This report replicates the LTQ functionality-integration analysis approach: a full, traceable issues

list plus a detailed write-up showing the exact trace steps used to derive every finding, so each

result can be reproduced cell-for-cell. The companion artefacts are:

| Artefact | Purpose |
| --- | --- |
| N2C_WBS_Issues_Register.xlsx | Formatted, filterable register — Summary tab + 5,055-row Issue List with cell references |
| N2C_WBS_Issues_List.csv | Same issues as plain CSV (full list) |
| analysis/audit.py | The reproducible analysis engine — re-run to regenerate every number in this report |

1. What the workbook is

The N2C Expanded WBS is a 5-year resource/effort model for a managed-service / secure-platform

programme. Each delivery area is a sheet (DLZ, Data Feeds, DARKSTAR OCD, AIP on ACHE Build & Sites

1–3, T&R on ACHE Site 2, Local Site, STRATA, NEXUS, BLACK KNIGHT, Service Management, NOC, Service

Desk, Security, Governance). Every delivery sheet shares an identical 24-column schema:

`

Column1 | Frequency | Optimistic | Most Likely | Pessimistic | Estimate |

Annual Effort (Days) | Annual Effort (% of FTE) | Total FTE to action |

Role 1 | SFIA | … | Role 5 | SFIA5 | Activity | Start Date | End Date | Contract Year | Team

`

1.1 The calculation model (reverse-engineered and verified)

The trace below establishes the rules every leaf row is expected to obey. These rules were validated

against known-good rows before being used to test the whole workbook.

| Field | Rule | Verification |
| --- | --- | --- |
| Estimate | PERT = (Optimistic + 4×MostLikely + Pessimistic) / 6 | DLZ R4: (5+40+15)/6 = 10 ✓ |
| Annual Effort (Days) | Estimate × Frequency-multiplier | DLZ R4: 10 × Monthly(12) = 120 ✓ |
| Annual Effort (% of FTE) | Annual Effort (Days) / 220 | 120 / 220 = 0.5455 ✓ |
| Total FTE to action | % of FTE × (number of named resources) | DLZ R4: 0.5455 × 2 roles = 1.0909 ✓ |
| Frequency multipliers | from Mapping tab | Fortnightly 26, Monthly 12, Weekly 52, Quarterly 4, Half-yearly 2, Yearly 1, One-off 1, Daily(Mon-Fri) 253, Daily(24×7) 365, Twice/Three-times-a-week 104/156 |

Headline positive: every computed field that *can* be checked against these rules is internally

consistent — 0 PERT errors, 0 Annual-Effort-Days errors, 0 %FTE errors across all 5,526 tasks.

The arithmetic engine is sound. All the issues below are about **data hygiene, resourcing logic, and

cross-tab integrity**, not broken formulas.

1.2 Programme totals derived from the model

| Metric | Value |
| --- | --- |
| Total annual effort (days, summed across all years) | 41,452 days |
| Total FTE-to-action (summed) | 304.3 FTE-years |
| Effort by contract year (days) | Y1 5,540 · Y2 8,383 · Y3 8,524 · Y4 9,664 · Y5 9,307 · (untagged 33) |
| Largest demand roles (FTE) | NOC Engineer 60.4 · Platform Engineer 45.1 · Infrastructure Engineer 39.3 · Security Engineer 20.2 · Security Architect 19.8 |

2. Methodology — how the analysis was run

Load the workbook with values resolved (data_only=True) so computed cells are read as their

stored results, not formulas.

Classify every row: a row is a leaf task if its Frequency cell is populated; rows with an

empty Frequency are section/activity headers and are skipped from arithmetic checks.

Track block context while scanning: any Column1 value containing CONTRACT YEAR n sets the

current block, so each leaf can be tested against the year it sits under.

Apply 14 validation rules (Section 4) to each leaf, recording every breach with its exact

Sheet!Row location and the evidence that triggered it.

Cross-tab checks: roles used in the WBS vs the Roles & SFIA master list; FTE roll-up vs the

summary tab; SFIA-level consistency for each role.

Calibrate noisy checks against ground truth — the contract-year and duplicate checks were

tightened (see 4.10 / 4.12) to eliminate false positives before publishing counts.

3. Issue summary

3.1 By severity & category

| Severity | Category | Count |
| --- | --- | --- |
| 🔴 High | End Date before Start Date | 2 |
| 🟠 Medium | Date stored as text (not a real date) | 4,696 |
| 🟠 Medium | Total FTE implies more resources than are named | 308 |
| 🟠 Medium | Contract Year disagrees with its block header | 19 |
| 🟠 Medium | Single resource loaded above 1.0 FTE | 5 |
| 🟠 Medium | WBS demand not reflected in Roles & SFIA roll-up | 4 |
| 🟡 Low | Same role used at inconsistent SFIA levels | 14 |
| 🟡 Low | Leaf task missing a Contract Year | 4 |
| 🟡 Low | Exact duplicate row | 3 |
|  | Total | 5,055 |

3.2 By sheet (excluding the bulk date-as-text rows, to expose real hotspots)

| Sheet | Issues (ex. date-text) | Note |
| --- | --- | --- |
| AIP on ACHE Build Years 2-4 | 153 | Systematic Total-FTE/role mismatch (see 4.5) |
| Local Site Years 1-2 | 28 | Contract-Year tagging errors |
| NEXUS Years 1-5 | 22 | Total-FTE/role mismatch |
| BLACK KNIGHT Years 1-5 | 20 | Total-FTE/role mismatch |
| Roles & SFIA | 18 | SFIA inconsistency + roll-up gaps |
| AIP Site 2 / T&R Site 2 | 16 / 16 | Total-FTE/role mismatch |
| Security Years 1-5 | 12 | End-before-start, over-allocation, duplicates |
| STRATA / AIP Site 3 / Governance | 12 / 12 / 11 | Mixed |

(Date-as-text dominates raw per-sheet counts; the 9 affected sheets are listed in 4.2.)

4. Findings with trace steps

Each finding states the rule, the trace (how the breach was detected), and evidence

(exact cells). Row numbers are the workbook's own 1-based rows.

4.1 🔴 End Date before Start Date — 2 occurrences

Rule: End Date ≥ Start Date.

Trace: parse both dates (handling the text-date format in 4.2) → compare → flag where end < start.

Evidence:

Security Years 1-5!R6 — *ITHC - DS OCD*: Start 2026-10-01, End 2026-07-01 (ends 3 months before it starts).

Service Management Years 1-5!R179 — *Process & Policy Review*: Start 2027-04-01, End 2027-01-01.

Impact: negative durations break any Gantt/scheduling roll-up and signal a copy-paste error in the

date columns. Fix: correct the End Date (likely 2027-07-01 and 2027-07-01 / next-FY respectively — confirm with the planner).

4.2 🟠 Dates stored as text, not real dates — 4,696 occurrences

Rule: date columns should hold real date values, not strings.

Trace: read each Start Date / End Date cell and test its Python type — datetime (good) vs

str like "15/03/2027" (bad). Tally per sheet.

Evidence — End Date is text on 9 of 17 sheets (every leaf row affected):

| Sheet | End-Date text rows |
| --- | --- |
| AIP on ACHE Site 2 Years 2-5 | 992 |
| T&R on ACHE Site 2 Years 2-5 | 992 |
| AIP on ACHE Site 3 Years 3-5 | 744 |
| DARKSTAR OCD Years 1-2 | 564 |
| AIP on ACHE Site 1 Years 4-5 | 496 |
| Governance Years 1-5 | 369 |
| Service Management Years 1-5 | 343 |
| Service Desk Years 1-5 | 115 |
| Security Years 1-5 | 80 |
| DLZ Years 1-5 | 1 (single stray text cell) |

The remaining 8 sheets store both dates correctly as date values — so the workbook is **internally

inconsistent**: identical columns are typed differently sheet-to-sheet.

Impact: text dates don't sort, don't feed date arithmetic, and silently corrupt any cross-sheet

timeline or MIN/MAX roll-up. The single stray DLZ!E… text cell is the most insidious — it looks

fine but one cell in a column of real dates will break a column-wide formula.

Fix: reformat the 9 sheets' date columns to real dates (Text-to-Columns / DATEVALUE), and fix

the one stray DLZ cell.

4.3 🟠 Total FTE implies more resources than are named — 308 occurrences

Rule: Total FTE to action = % of FTE × (number of Role columns populated), so

Total FTE ÷ % of FTE should equal the count of named roles.

Trace: for each leaf compute ratio = Total FTE ÷ % of FTE, round to nearest integer = *implied

resource count*, compare to the number of populated Role1–Role5 cells.

Distribution of the mismatch:

| Roles named | Resources implied by Total FTE | Rows |
| --- | --- | --- |
| 1 | 2 | 65 |
| 1 | 3 | 98 |
| 1 | 5 | 30 |
| 2 | 3 | 72 |
| 2 | 5 | 35 |
| 3 | 4 | 8 |

Evidence: AIP on ACHE Build Years 2-4!R4 *Active Directory* — Total FTE = 3 × %FTE but only one

role (*Infrastructure Engineer*) is named; same for ADFS/Beyond Trust/Tenable (R5–R7). DLZ!R25

*Configuration Management* — Total FTE = 2 × %FTE, one *Platform Engineer* named.

Impact: either the Role columns are under-populated (real people missing from the plan) or the

Total FTE is overstated (double-counted demand). 153 of the 308 are in *AIP on ACHE Build* — a

systematic pattern in that sheet, not scattered typos. This directly distorts the 304-FTE programme

total. Fix: decide the intended rule per row and reconcile — name the missing resources or

recompute Total FTE from the named roles.

4.4 🟠 Contract Year disagrees with its block header — 19 occurrences

Rule: a leaf's Contract Year should match the CONTRACT YEAR n block it sits under.

Trace: carry the current block's year while scanning; flag leaves whose Contract Year differs.

Evidence: all under Local Site - CONTRACT YEAR 1: rows tagged Year 2 (R4–R7, R9–R11) and Year 3

(R14–R17, R19…) — e.g. Local Site!R4 *Switch Maintenance* tagged Year 2 inside the Year-1 block,

with a Year-1 start date (2026-10-01). STRATA shows the same pattern (Pre-Prod QA / Pipeline

Sustainment tagged Years 2–3 in the Year-1 block).

Impact: per-year effort roll-ups mis-bucket this work. The untagged 33 days in §1.2 and these 19

mis-tagged rows mean the Y1–Y5 split is not fully trustworthy until reconciled. Fix: align the

Contract Year cell to the block, or split the rows into the correct year blocks.

4.5 🟠 Single resource loaded above 1.0 FTE — 5 occurrences

Rule: a task with one named resource cannot need more than 1.0 FTE of that resource.

Trace: flag leaves where roles named = 1 and Total FTE > 1.0.

Evidence: Security Years 1-5!R7, R25, R44, R64, R84 — *Security Assurance (SbD & 453)*, each

1.63 FTE against a single *Security Architect* (Daily, 358 days/yr). One named person cannot

deliver 1.63 FTE.

Impact: the role is structurally under-resourced every year — this needs ~2 Security Architects,

not 1, or the daily estimate is too high. Fix: add the second resource or re-scope the estimate.

4.6 🟠 WBS demand not reflected in the `Roles & SFIA` roll-up — 4 occurrences

Rule: a role carrying real FTE in the WBS should show non-zero demand in the Roles & SFIA

summary tab.

Trace: sum each role's FTE across all leaves; cross-check the role's row on Roles & SFIA; flag

where WBS FTE > 0.05 but the summary row is all zeros.

Evidence: *Security Architect* ~19.8 FTE in the WBS but 0 in summary (Roles & SFIA!R27);

*Service Management Controller* ~12.8 FTE but the master row (R41) is entirely blank; *Software

Lead* ~0.83 and *Business Analyst* ~1.32 likewise 0.

Impact: the summary/Overview tabs are stale — they understate demand for at least these

roles, so any headcount or cost number taken from them is wrong. The Overview tab is itself only

"DLZ Contract Year 1" and almost entirely zeros, i.e. a partial roll-up that was never completed.

Fix: rebuild the roll-up from the live WBS (e.g. SUMIFS by role), and populate the blank

*Service Management Controller* master row.

4.7 🟡 Same role used at inconsistent SFIA levels — 14 roles

Trace: collect the set of SFIA levels each role name is paired with across all leaves; flag roles

with >1 distinct level.

Evidence (examples): *Platform Engineer* → SFIA 3/4/5/6; *Software Dev* → 3/4/5; *Service Desk

Analyst* → 2/3/4; *Security Architect* → 4/5/6; *Service Management Controller* → 2/3.

Impact: mostly legitimate (seniority varies by task) but it prevents a clean role-rate roll-up and

should be confirmed deliberate rather than data drift — especially where the same activity name uses

different levels.

4.8 🟡 Leaf task missing a Contract Year — 4 occurrences

Evidence: AIP on ACHE Site 1!R228 *Active Directory*; Service Management!R24 *Data Feeds*,

R52 *Problem Reporting*, R140 *Problem Analysis & Prioritisation*. These contribute the 33

"untagged" days in §1.2. Fix: set the Contract Year.

4.9 🟡 Exact duplicate rows — 3 occurrences

Trace: hash all 24 columns of each leaf within a sheet; flag identical rows.

Evidence: Security Years 1-5 — R81=R61, R82=R62, R83=R63 (*ITHC - AIP on Site 2 / 3 / 1*). The

ITHC block appears twice verbatim. Impact: double-counts ITHC effort. Fix: delete the

duplicate set (or confirm the second instance belongs to a different year/site and differentiate it).

4.10 Calibration note — checks tightened to remove false positives

Two checks were deliberately narrowed so the published counts are trustworthy:

Contract Year: an initial date-derived heuristic produced ~4,400 hits because build sheets start

off-cycle (Aug) and year boundaries vary. Replaced with the block-header comparison → 19 real

hits (4.4).

Duplicates: a partial-key match flagged ~1,540 rows that are legitimately repeated per-tool

maintenance lines. Replaced with all-24-columns-identical → 3 real duplicates (4.9).

4.11 Checks that passed cleanly (negative results worth recording)

PERT estimate vs (O+4ML+P)/6 — 0 breaches.

Annual Effort (Days) vs Estimate × multiplier — 0 breaches.

Annual Effort (% FTE) vs Days / 220 — 0 breaches.

Three-point ordering O ≤ ML ≤ P — 0 breaches.

Unknown/blank frequencies — 0 (every Frequency resolves against the Mapping tab).

Roles absent from the master list — 0 (every role used exists in Roles & SFIA).

5. Prioritised remediation plan

| # | Action | Addresses | Effort |
| --- | --- | --- | --- |
| 1 | Fix the 2 end-before-start dates | 4.1 (High) | Trivial |
| 2 | Convert text dates → real dates on the 9 sheets; fix the 1 stray DLZ cell | 4.2 (4,696) | Low (bulk) |
| 3 | Reconcile Total FTE vs named roles, starting with AIP Build (153 rows) | 4.3 (308) | Medium — needs planner input |
| 4 | Re-tag the 19 mis-yeared rows + 4 missing-year rows to their block | 4.4 / 4.8 | Low |
| 5 | Resolve the 5 over-1-FTE Security Architect lines (add resource or re-scope) | 4.5 | Decision |
| 6 | Rebuild Roles & SFIA / Overview roll-ups from the live WBS | 4.6 | Medium |
| 7 | Remove the 3 duplicate ITHC rows | 4.9 | Trivial |
| 8 | Confirm intended SFIA levels per role | 4.7 | Review |

Bottom line: the model's maths is solid, but the plan is not yet decision-ready. The text-date

typing (4.2), the 308 Total-FTE/role discrepancies (4.3), and the stale roll-up tabs (4.6) mean any

headcount, cost, or timeline figure read straight from the workbook today will be wrong. Items 1–4 and

7 are quick mechanical fixes; items 3, 5 and 6 need a planner's decision before the 304-FTE / 41,452-day

totals can be trusted.

*Full line-by-line issue list: N2C_WBS_Issues_Register.xlsx (Issue List tab) and N2C_WBS_Issues_List.csv.

Re-run analysis/audit.py against the source workbook to regenerate every figure in this report.*